March 3, 2022

4:00-5:00 PM EST

RHO Implementation Monthly Investigator Call Minutes

| Invitees/Attendees: |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Dr. Larry Rhein, Principal Investigator |  | Boston Children’s Hospital |  | Maria Fareri Children’s Hospital |  |
| Heather White, Project Coordinator |  | Children’s Hospital of Philadelphia |  | Massachusetts General Hospital |  |
| Lindsey Simoncini, Research Coordinator |  | Cincinnati Children’s Hospital |  | Nationwide Children’s Hospital |  |
| Crystal Vasquez, Research Assistant |  | National Jewish Health, Colorado |  | Peyton Manning Children’s Hospital |  |
| Arkansas Children’s Hospital |  | Dartmouth-Hitchcock Medical Center |  | U. of California, San Diego |  |
| U. of Kentucky Children’s Hospital |  | University of Maryland |  | Vanderbilt |  |

Next Investigator Meeting will be on April 7th at 4pm EST

Start Up Progress/ Enrollment

- 13/14 sites have contracts executed

- Waiting on IRB approval from 4/14 sites

  - Heather will be sending weekly emails to sites who remain inactive inquiring about their site’s status/ estimated timeline to begin enrollment

- Our goal was to reach 33% of all eligible families by February 2022 – currently we can not accurately estimate the reach of the program due to missing screening and eligibility

  - Emphasized that all infants who are eligible despite their participation status in the RHO program should be documented to capture the true N of the program

Barriers to Enrollment/ Projected vs Actual Enrollment

- Discussion around the possible barriers that have affected the enrollment numbers of the program

  - Are low enrollment numbers due to?

    - Change in demographics of infants going home on supplemental oxygen?

    - Did sites/ RHO team overestimate their site enrollment numbers at implementation initiation?

    - Improvement in NICU care (development of new guidelines/protocols) which in turn is increasing NICU LOS and decreasing the utilization of LFNC?

  - Goal is to try to understand why sites aren’t meeting their original estimate of projected enrollments

REDCap Documentation/ Upcoming Modifications

- Emphasized that all eligible families should receive a fact sheet and have a completed screening and eligibility and demographics form in the REDCap

  - For infants who are eligible to be followed but aren’t followed by the program but opt-in to data sharing, sites are still responsible for filling-out a screening and eligibility form, demographics form, adverse events form and implementation at discharge form

- PPHN Medication therapy Modification

  - Plan is to add a follow-up question to the first inclusion criteria regarding the patient’s pulmonary hypertension medication therapy status

  - This will allow us to capture the true N of infants excluded due to PPHN specific medication therapy for future analysis

- RAD 97 Alarm Parameters Modification

  - Dr. Sara Dumero from CHOP is working on a project which focuses on the different alarm parameters on the RAD 97 oximeters

  - Heather will send around survey to all sites regarding their site-specific guidelines for RAD 97 alarm parameters

Implementation Related Problems

This past month most of the problems have been associated with RAD 97 devices. Specifically, either devices not being properly configured or equipment issues.

- Masimo

  - We are working with Masimo to eliminate the persistent connectivity issues and better streamline the onboarding process across all sites

  - Our goal is to resolve any device related issues (i.e., configuration, Wi-Fi connectivity, damaged equipment etc.) within a week of problem identification

  - Masimo is working with homecare companies to configure all devices even if they aren’t being used specifically for the RHO program to further minimize the frequency of configuration issues

- Homecare Company Readiness

  - Some homecare companies have been trained over a year ago. Masimo will initiate re-education sessions with all home cares

    - Please make sure to give your homecare companies at least a week’s notice when there is a potential discharge as a new site coming on board. This will further aid in preparation and coordination in the discharge planning with homecare companies

    - For those sites who have yet to enroll their first patient, homecare companies have advised to reach out to them in advance to ensure they have RAD 97’s available and the devices are properly configured

Variation in Discharge Flowrate

The RHO program at UMass has been operating within set oxygen flow rate parameters with the highest discharge flow rate being 1L/min and the lowest being 125 cc/min. Patients wean in 50% decrements, to a minimum flow rate of 125 cc/min of nocturnal oxygen. To provide the most accurate recommendation based off the RHO algorithm, it is recommended that all patients followed by the RHO program adhere to the set flow rate parameters. Due to an increase in flow rate variations across sites, standardization of flow rates at discharge should be discussed.

- Site Discussion/ Consensus

  - Moving forward we will manage and analyze the data of infants discharged on a flowrate less than 125 cc/min in the following ways:

    - If an infant is on a flowrate less than 125 cc/min at time of discharge, we will strongly encourage the clinical team to increase their oxygen up to 125 cc/min

    - If a patient is being managed on less than 125 cc/min and their bi-weekly report suggest either an increase or wean, the recommendation will be to increase or wean to a flowrate that is in accordance with the program’s algorithm

    - If a patient is being managed on less than 125 cc/min any wean below 125 cc/min will not count as a “wean” in final data analysis

    - Infants who were managed on a flowrate outside of our pre-set parameters will be grouped and analyzed separately

  - Emphasized the importance of standardization across all sites to ensure the accuracy and validity of the implementation findings at the end of the study

  - Heather sent an email to all sites outlining how we will manage infants who are discharged on less than 125 cc/min

Parent Advisory Board Meeting

- The Parent Advisory Board Meeting will take place in the upcoming weeks

- Our goal is to have a least one parent representative from each site to ensure diversity and create spread geographically

Invoicing/Subcontracts

- Our grants office will be reaching out to all sites over the next few weeks

- Please notify Heather who will be the primary delegate at your site

- If you have not received funds for year 1, please make sure to invoice our grants office as soon as possible

- Year 2 subcontract funds will be sent out to all sites in the upcoming weeks

  - NOTE: Unused funds from year 1 carry over to year 2

*Home care companies serving multiple sites, the number of counts is shared between sites.

RAD 97s Count

Site Start-Up Progress

| Wave | Site # | Site Name | Contract Executed |  | cIRB Approval | Local IRB Approval | Regulatory Documents | pSite Communication Plan Agreement | REDCap Access |  | Site Training Comple | First Enrollment Date | Download Schedule |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Wave 1 | 102 | Boston Children's Hospital |  | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ |  | 7/8/2021 | M/Th |
|  | 106 | Dartmouth-Hitchcock |  | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ |  |  | T/F |
|  | 107 | Maria Fareri Children's |  | ᴏ | N/A | ᴏ | ᴏ | N/A | ᴏ | ᴏ |  | 11/19/2021 | M/Th |
|  | 108 | Massachusetts General Hospital |  | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ |  | 7/8/2021 | M/Th |
|  | 113 | University of Maryland |  | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ |  | 8/23/2021 | M/Th |
|  | 114 | Vanderbilt |  | ᴏ | N/A | ᴏ | ᴏ | N/A | ᴏ | ᴏ |  |  | T/F |
| Wave 2 | 101 | Arkansas Children's Hospital |  | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ |  | 11/12/2021 | M/Th |
|  | 103 | Children's Hospital of Phil. |  | ᴏ | N/A | ᴏ | ᴏ | N/A | ᴏ | ᴏ |  |  | TBD |
|  | 104 | Cincinnati Children's Hospital |  | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ |  |  | TBD |
|  | 105 | National Jewish Health |  | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ |  |  | TBD |
|  | 109 | Nationwide Children's Hospital |  | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ |  | 3/7/2022 | TBD |
|  | 110 | Peyton Manning Children's Hospital |  | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ |  |  | TBD |
|  | 111 | U. of California, San Diego |  | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ |  | 11/12/2021 | M/Th |
|  | 112 | U. of Kentucky Children's Hospital |  | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ |  |  | M/Th |