December 2, 2021

4:00-5:00 PM EST

RHO Implementation Monthly Investigator Call Minutes

| Invitees/Attendees: |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Dr. Larry Rhein, Principal Investigator |  | Boston Children’s Hospital |  | Maria Fareri Children’s Hospital |  |
| Heather White, Project Coordinator |  | Children’s Hospital of Philadelphia |  | Massachusetts General Hospital |  |
| Lindsey Simoncini, Research Coordinator |  | Cincinnati Children’s Hospital |  | Nationwide Children’s Hospital |  |
| Maria Matoshi, Research Assistant |  | National Jewish Health, Colorado |  | Peyton Manning Children’s Hospital |  |
| Arkansas Children’s Hospital |  | Dartmouth-Hitchcock Medical Center |  | U. of California, San Diego |  |
| U. of Kentucky Children’s Hospital |  | University of Maryland |  | Vanderbilt |  |

RHO Program Timeline

- All site trainings have been completed

- 11/14 sites have their contracts executed

Enrollment

- Total of 16 patients are currently enrolled in the RHO program

- The average duration of home oxygen therapy is currently 61 ± 29 days across active implementation sites

- Our enrollment numbers are increasing, however, they are still below our projected enrollment

  - Discussion around new trends in birth rates and discharge patterns

REDCap Data Access Group (DAG)

- Team members responsible for the RHO program data entry should complete a REDCap user request form if they haven’t done so already

- Detailed instructions are available on our website

- 9/14 sites have access to their DAG

- 4/6 active implementation sites have entered data into REDCap

  - Demographic forms are important for the accuracy of the overall denominator

Implementation Related Problems

This month most of the problems have been associated with devices. Specifically, either devices not being properly configured or homecare companies not being ready for “Go-Live”

- RAD 97 Configuration

  - The only way for us to know if the device is properly configured is by looking at the color of the wi-fi symbol once the device is connected to the internet.

  - If the color is green the device is communicating properly with the UMass SafetyNet, if it is blue, then the device is not configured and needs to be swapped (or configured by the DME) as soon as possible

- Homecare company readiness

  - Some homecare companies have been trained over a year ago. Masimo will initiate re-education sessions with all home cares

  - Home care companies need to be able to test whether their devices are configured before sending them back to Masimo, and should reach out to their local Masimo account manager for assistance if the devices are found to be not configured

  - Home care companies will be advised to try connecting the devices to WIFI prior to disseminating to patients

Oximetry Reports Compliance and Deviation Types

- Compliance

- Our goal is to have at least 90% compliance with the algorithm determination across all sites

- Over the next few months we will be paying close attention to deviation types, specifically for infants on higher flow rates to see if there are consistent patterns requiring the algorithm to be modified

- We track deviation types purely for quality improvement purposes. We hope that this data will help us optimize the RHO algorithm and identify populations for which the program works best.

- The most common category of the deviation type is “no data was captured”

- Unfortunately, there is no way for us to find out whether the reason for no data is WIFI connection or the patient is simply not wearing their oximeter

RHO NICU Graduate Music Class

- We are excited to invite families across all sites to participate in our UMass NICU Graduate Music Class

- Please, find the flyer attached

Next Investigator Meeting will be on January 6th at 4pm EST

*Home care companies serving multiple sites, the number of counts is shared between sites.

*Home care companies serving multiple sites, the number of counts is shared between sites.

RAD 97s Count

Site Start-Up Progress

| Wave | Site # | Site Name | Contract Executed |  | cIRB Approval | Local IRB Approval | Regulatory Documents | pSite Communication Plan Agreement | REDCap Access |  | Site Training Comple | First Enrollment Date | Download Schedule |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Wave 1 | 102 | Boston Children's Hospital |  | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ |  | 7/8/2021 | M/Th |
|  | 106 | Dartmouth-Hitchcock |  | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ |  |  | T/F |
|  | 107 | Maria Fareri Children's |  | ᴏ | N/A | ᴏ | ᴏ | N/A | ᴏ | ᴏ |  | 11/19/2021 | M/Th |
|  | 108 | Massachusetts General Hospital |  | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ |  | 7/8/2021 | M/Th |
|  | 113 | University of Maryland |  | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ |  | 8/23/2021 | M/Th |
|  | 114 | Vanderbilt |  | ᴏ | N/A | ᴏ | ᴏ | N/A | ᴏ | ᴏ |  |  | T/F |
| Wave 2 | 101 | Arkansas Children's Hospital |  | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ |  | 11/12/2021 | M/Th |
|  | 103 | Children's Hospital of Phil. |  | ᴏ | N/A | ᴏ | ᴏ | N/A | ᴏ | ᴏ |  |  | TBD |
|  | 104 | Cincinnati Children's Hospital |  | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ |  |  | TBD |
|  | 105 | National Jewish Health |  | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ |  |  | TBD |
|  | 109 | Nationwide Children's Hospital |  | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ |  |  | TBD |
|  | 110 | Peyton Manning Children's Hospital |  | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ |  |  | TBD |
|  | 111 | U. of California, San Diego |  | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ |  | 11/12/2021 | M/Th |
|  | 112 | U. of Kentucky Children's Hospital |  | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ |  |  | M/Th |