April 1, 2021

4-5:00 PM EST

RHO Implementation Monthly Investigator Call Minutes

| Invitees/Attendees: |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Dr. Larry Rhein, Principal Investigator |  | Boston Children’s Hospital |  | Maria Fareri Children’s Hospital |  |
| Heather White, Project Coordinator |  | Children’s Hospital of Philadelphia |  | Massachusetts General Hospital |  |
| Lindsey Simoncini, Research Assistant |  | Cincinnati Children’s Hospital |  | Nationwide Children’s Hospital |  |
| Maria Matoshi, Research Assistant |  | National Jewish Health, Colorado |  | Peyton Manning Children’s Hospital |  |
| Arkansas Children’s Hospital |  | Dartmouth-Hitchcock Medical Center |  | U. of California, San Diego |  |
| U. of Kentucky Children’s Hospital |  | University of Maryland |  | Vanderbilt |  |

Site Trainings

- 5/6 Wave 1 site trainings have been scheduled; Wave 2 site trainings are being scheduled for this summer

- Please let the UMass team know any COVID-19 restrictions/limitations your site has that may conflict with the trainings

IRB/Regulatory

- UMass has approved the IRB and will serve as the central IRB

- Each site’s local IRB will need to cede approval to UMass

- SMART IRB will be used

  - Each site will upload their versions of the fact sheet and investigator study plan

  - Email sent out 4/5/21 with additional documents requested from site IRBs

  - Heather and Lindsey are available to help with this process

DME Companies

- UMass and Masimo have been working on identifying each sites’ DME companies

- Goal is for each site to have 2-3 DME companies that offer RAD 97s so as many infants are eligible for the program as possible

Next Investigator Meeting will be on May 6th at 4pm EST