June 3, 2021

4-5:00 PM EST

RHO Implementation Monthly Investigator Call Minutes

| Invitees/Attendees: |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Dr. Larry Rhein, Principal Investigator |  | Boston Children’s Hospital |  | Maria Fareri Children’s Hospital |  |
| Heather White, Project Coordinator |  | Children’s Hospital of Philadelphia |  | Massachusetts General Hospital |  |
| Lindsey Simoncini, Research Assistant |  | Cincinnati Children’s Hospital |  | Nationwide Children’s Hospital |  |
| Maria Matoshi, Research Assistant |  | National Jewish Health, Colorado |  | Peyton Manning Children’s Hospital |  |
| Arkansas Children’s Hospital |  | Dartmouth-Hitchcock Medical Center |  | U. of California, San Diego |  |
| U. of Kentucky Children’s Hospital |  | University of Maryland |  | Vanderbilt |  |

Site Trainings

- All Wave 1 site trainings have been completed; 4 out of 8 Wave 2 site trainings have been scheduled. We are still waiting on confirmations from the remaining 4 sites. Please let us know your availability so we can plan meetings with your homecare companies as well.

IRB/regulatory

- SMART IRB

  - Each site needs to upload their modified versions of the fact sheet and investigator study plan.

  - We can make modifications to the SMART IRB only after the initially selected 10 sites cede their approval to UMMS. Once this is completed, we will add the remaining sites.

- If your IRB is requiring written informed consent, do not cede approval to UMMS.

- Referral Hospitals may need a separate IRB if they are providing VON data. Heather is working on the protocol.

- pSite forms will be disseminated once site IRB has ceded approval.

- All contracts will be back dated to February.

Home Care Companies

- Masimo will help ensure that each site has 2-3 home care companies providing RAD 97.

Site progress on Implementation Start-Up

- Please send your current list of study personnel and CITI certificates to Maria Matoshi.

Collaboration Project

- Submit potential spin-off project ideas to Heather and Dr. Rhein

Next Investigator Meeting will be on July 1st at 4pm EST