July 1, 2021

4-5:00 PM EST

RHO Implementation Monthly Investigator Call Minutes

| Invitees/Attendees: |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Dr. Larry Rhein, Principal Investigator |  | Boston Children’s Hospital |  | Maria Fareri Children’s Hospital |  |
| Heather White, Project Coordinator |  | Children’s Hospital of Philadelphia |  | Massachusetts General Hospital |  |
| Lindsey Simoncini, Research Assistant |  | Cincinnati Children’s Hospital |  | Nationwide Children’s Hospital |  |
| Maria Matoshi, Research Assistant |  | National Jewish Health, Colorado |  | Peyton Manning Children’s Hospital |  |
| Arkansas Children’s Hospital |  | Dartmouth-Hitchcock Medical Center |  | U. of California, San Diego |  |
| U. of Kentucky Children’s Hospital |  | University of Maryland |  | Vanderbilt |  |

Site Trainings

- All Wave 1 site trainings have been completed.

- 4 out of 8 Wave 2 site trainings have been scheduled.

- Masimo is coordinating times to meet with sites’ home care companies. Heather presenting to acute home care’s on July 21st.

IRB/regulatory

- Due to delays in SMART IRB submissions of wave 2 sites start the process with your IRB in the meantime.

  - You may also choose to complete your IRB as an independent site.

- If your IRB is requiring written informed consent, do not cede approval to UMMS.

- Heather completed the protocol for referral hospitals that require a separate IRB for providing VON data. Reach out to her if you need any help.

- pSite forms will be disseminated once an individual site IRB has ceded approval to UMMS.

Home Care Companies

- Masimo will help ensure that each site has 2-3 home care companies providing RAD 97.

- 57% of sites meet our target goal.

- National home care companies such as Lincare, Apria and Promptcare are interested in joining at the smaller branch level. More updates to come.

Site progress on Implementation Start-Up

- Please send your current list of study personnel and CITI certificates to Maria Matoshi as part of the regulatory documents’ requirement.

- Refer to Site Progress table on Page 4

REDCap User Access Groups

- Lindsey will send out the instruction sheet on how to fill out REDCap forms. It will also be included on our website:

https://www.umassmed.edu/rho-program/

Login: RHO

Password: Oximetry14

- Notify Lindsey and Heather once you have been granted UMass REDCap approval to be added to your site’s data access group.

Timing of Data Collection

- The goal is to send VON and additional outpatient variable data within 3 months of onset of implementation.

- Implementation data:

  - Screening and eligibility form should be filled out prior to NICU discharge.

  - Demographics form should be filled out around the time of NICU discharge. Pulmonary Hypertension diagnosis is particularly important since it changes the RHO algorithm for weaning.

    - We are going to add a diuretics section to this form.

  - Home Oxygen Data Form will be filled out in real time by your DCC. Important to provide response on action taken to oxygen flow rate.

  - Adverse events will be followed for 6 months post HOT discontinuation. Adverse events include both respiratory and non-respiratory emergency department visits, urgent care visits, and hospitalizations.

    - Dates and reminders of this data collection will be provided in your sites monthly report.

The RHO Algorithm

| Figure 1: RHO OXYGEN WEANING PARAMETERS |  |  |
| --- | --- | --- |
|  | STANDARD OXYGEN MANAGEMENT GROUP | RHO OXYGEN MANAGEMENT GROUP |
| CRITERIA FOR INCREASING O2 FLOW RATE | INABILITY TO MAINTAIN O2 SAT >93% AT PATIENT’S CURRENT O2 LEVEL FOR 20 MINUTES IN CLINIC VISIT CHALLENGE | INABILITY TO MAINTAIN O2 SAT >93% FOR >95% OF RECORDED TIME |
| CRITERIA FOR MAINTAINING CURRENT O2 FLOW RATE | ABILITY TO MAINTAIN O2 SAT >93% AT PATIENT’S CURRENT O2 BUT UNABLE TO MAINTAIN O2 SAT >93% AT WEANED FLOW RATE FOR 20 MINUTES IN CLINIC VISIT CHALLENGE | ABILITY TO MAINTAIN O2 SAT >93% FOR >=95% OF RECORDED TIME BUT UNABLE TO MAINTAIN O2 SAT >96% FOR >=95% OF RECORDED TIME |
| CRITERIA FOR WEANING O2 FLOW RATE | ABILITY TO MAINTAIN O2 SAT >96% AT WEANED FLOW RATE FOR 20 MINUTES IN CLINIC VISIT CHALLENGE | ABILITY TO MAINTAIN O2 SAT > 96% FOR >=95% OF RECORDED TIME |
| ** RHO pass and fail will be determined by assessment of recorded oximetry. For each episode of transmitted data, a minimum of 1500 minutes of recorded data, will be required for analysis to make any determination. *** Infants followed by the RHO program will also receive monthly in-clinic weaning attempts |  |  |

Next Investigator Meeting will be on August 5th at 4pm EST

| Implementation Wave | Site # | Site Name | Contract Executed | cIRB Approval | Local IRB Approval | Regulatory Documents | pSite Communication Plan Agreement | REDCap Access | Site Training Completed | Site Implementation Date | First Enrollment Date | Downloading Schedule |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Wave 1 | 102 | Boston Children's Hospital | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | 6/1/2021 |  | M/T |
|  | 106 | Dartmouth-Hitchcock | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | 6/1/2021 |  | T/F |
|  | 107 | Maria Fareri Children's | ᴏ | N/A | ᴏ | ᴏ | N/A | ᴏ | ᴏ | 6/1/2021 |  | M/T |
|  | 108 | Massachuesetts General Hospital | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | 6/1/2021 |  | M/T |
|  | 113 | University of Maryland | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | 6/1/2021 |  | M/T |
|  | 114 | Vanderbilt | ᴏ | N/A | ᴏ | ᴏ | N/A | ᴏ | ᴏ | 6/1/2021 |  | T/F |
| Wave 2 | 101 | Arkansas Children's Hospital | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | 8/1/2021 |  | TBD |
|  | 103 | Children's Hospital of Phil. | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | 8/1/2021 |  | TBD |
|  | 104 | Cincinnati Children's Hospital | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | 8/1/2021 |  | TBD |
|  | 105 | National Jewish Health | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | 8/1/2021 |  | TBD |
|  | 109 | Nationwide Children's Hospital | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | 8/1/2021 |  | TBD |
|  | 110 | Peyton Manning Children's Hospital | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | 8/1/2021 |  | TBD |
|  | 111 | U. of California, San Diego | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | 8/1/2021 |  | TBD |
|  | 112 | U. of Kentucky Children's Hospital | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | 8/1/2021 |  | TBD |