May 5th, 2022

4:00-5:00 PM EST

RHO Implementation Monthly Investigator Call Minutes

| Invitees/Attendees: |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Dr. Larry Rhein, Principal Investigator |  | Boston Children’s Hospital |  | Maria Fareri Children’s Hospital |  |
| Heather White, Project Coordinator |  | Children’s Hospital of Philadelphia |  | Massachusetts General Hospital |  |
| Lindsey Simoncini, Research Coordinator |  | Cincinnati Children’s Hospital |  | Nationwide Children’s Hospital |  |
|  |  | National Jewish Health, Colorado |  | Peyton Manning Children’s Hospital |  |
| Arkansas Children’s Hospital |  | Dartmouth-Hitchcock Medical Center |  | U. of California, San Diego |  |
| U. of Kentucky Children’s Hospital |  | University of Maryland |  | Vanderbilt |  |

Startup/progress

- Only 2 more sites to be activated, awaiting IRB approval

Enrollment

- A total of 41 babies followed to date, 17 have weaned with an average HOT duration of 71 days

- Primary reason for exclusion from program = RAD 97 unavailable

  - Working with Masimo to supply more homecare companies with RAD 97’s

  - Please try to refer eligible babies to home care companies in your area that have RAD 97’s available

- Should be enrolling about 15 babies per month, currently the average enrollment per month is 3.7 babies

Projected vs Actual N of Infants Being Followed

- Seen a dip in enrollment across all active site’s, discussions around potential factors for this

- Have discussed potential factors contributing to low enrollment numbers

Barriers to Enrollment

- Please continue to screen all potentially eligible babies being discharged on supplemental oxygen therapy

- Monthly site report’s rely on demographic forms being complete

Upcoming IRB Submission

- Original project plan included adding parental/family survey’s once in the intensive implementation phase, study submitted to UMMS IRB

- Will send all appropriate documents to all sites once receive IRB approval

Recent Modification Approval to the Study Plan

- Clarification on serious adverse event definition approved by UMass IRB. Any adverse event that is, in the opinion of the investigator, expected of a former preterm infant on HOT will not count as a serious adverse event (SAE).

- Please report all adverse events within 72 hours of their occurrence or the site becoming aware of event.

Homecare Readiness

- For new sites coming on board or for the first referral to a particular home care try to provide 2-weeks’ notice so that they can refamiliarize themselves with the program and equipment

Non-Compliance with the RHO Algorithm

- There has been a total of 854 data reports, and 309 (36%) have a deviation reported

- A total of 55 new deviations have occurred this past month, and the most frequent deviation type was “Provider not Following Guideline” (22 new deviations)

- 16 infants had more than one report with the recommendation not being followed

- 4% of reports, the provider has felt comfortable maintaining when the algorithm suggested an increase in oxygen flow rate

Invoicing

- Reminder to submit invoice to the UMMS grant’s office

Next Investigator Meeting will be on June 2nd at 4pm EST

*Home care companies serving multiple sites, the number of counts is shared between sites.

RAD 97s Count