June 2nd, 2022

4:00-5:00 PM EST

RHO Implementation Monthly Investigator Call Minutes

| Invitees/Attendees: |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Dr. Larry Rhein, Principal Investigator |  | Boston Children’s Hospital |  | Maria Fareri Children’s Hospital |  |
| Heather White, Project Coordinator |  | Children’s Hospital of Philadelphia |  | Massachusetts General Hospital |  |
| Lindsey Simoncini, Research Coordinator |  | Cincinnati Children’s Hospital |  | Nationwide Children’s Hospital |  |
| Arkansas Children’s Hospital |  | National Jewish Health, Colorado |  | Peyton Manning Children’s Hospital |  |
| U. of Kentucky Children’s Hospital |  | Dartmouth-Hitchcock Medical Center |  | U. of California, San Diego |  |
|  |  | University of Maryland |  | Vanderbilt |  |

Startup/progress

- Only 2 more sites to be activated, awaiting IRB approval

Enrollment

- A total of 53 babies followed to date, 21 have weaned with an average HOT duration of 69 days

- Primary reason for exclusion from program = RAD 97 unavailable

  - Working with Masimo to supply more homecare companies with RAD 97’s

  - Please try to refer eligible babies to home care companies in your area that have RAD 97’s available

  - Currently some of our more active home care companies do not have RAD 97’s available as they are waiting on equipment deliveries. Masimo is reporting a 5–7-week delay in shipping. In the meantime, referrals may have to be placed with home cares in your area with equipment on their shelves.

- Should be enrolling about 15 babies per month, currently the average enrollment per month is 4.6 babies

Projected vs Actual N of Infants Being Followed

- Seen a dip in enrollment across all active site’s, discussions around potential factors for this

- Have discussed potential factors contributing to low enrollment numbers, and this maybe due to higher estimates in grant planning

Barriers to Enrollment

- Please continue to screen all potentially eligible babies being discharged on supplemental oxygen therapy

  - This will help us identify the true population of infants on HOT

- Monthly site reports rely on the demographic forms being complete for each subject

Family Satisfaction Survey

- The project has been submitted and approved as non-human subject research by UMMS IRB

- Heather will be sending out all project materials to upload to your IRB. UMMS can serve as the central IRB but it may be a quicker process if each site oversees their own. Please contact Heather with any questions or if your site will not be ceding to UMMMS.

Increase in Providers Not Following the RHO Algorithm

- Providers are noticing an increase in the time spent below each target saturation for older more active patients, in these cases they are not following when the time below 93% suggests an increase but the time below 90% is within acceptable range.

- Discussion around when infants are more active and can pull cannula out of their nose – will keep track of how often this occurring

  - Dr. Nelson from MGH mentioned that he has been calculating the actual minutes that influenced the time below 93% and if this time is over what parents report for time off cannula he has not been increasing. Heather to investigate adding this to python report.

RHO Data and Spin Off Projects

- Please complete the Spin Off Project Survey if you have not done so already

- Heather will be pulling information on the N of patients that require an increase immediately after NICU discharge

- If you have a potential project idea, please reach out to Heather and Larry

Homecare Readiness

- For new sites coming on board or for the first referral to a particular home care try to provide 2-weeks’ notice so that they can refamiliarize themselves with the program and equipment

Invoicing

- Reminder to submit invoice to the UMMS grant’s office

Next Investigator Meeting will be on July 7th at 4pm EST

*Home care companies serving multiple sites, the number of counts is shared between sites.

RAD 97s Count