# June 1st, 2023

4:00-5:00 PM EST

RHO Implementation Monthly Investigator Call Minutes

| Invitees/Attendees: |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Dr. Larry Rhein, Principal Investigator |  | Boston Children’s Hospital |  | Maria Fareri Children’s Hospital |  |
| Heather White, Project Coordinator |  | Children’s Hospital of Philadelphia |  | Massachusetts General Hospital |  |
| Lindsey Simoncini, Research Coordinator |  | Cincinnati Children’s Hospital |  | Nationwide Children’s Hospital |  |
| Katie Edeburn, Research Assistant |  | National Jewish Health, Colorado |  | Peyton Manning Children’s Hospital |  |
| Arkansas Children’s Hospital |  | Dartmouth-Hitchcock Medical Center |  | U. of California, San Diego |  |
| U. of Kentucky Children’s Hospital |  | University of Maryland |  | Vanderbilt |  |

Enrollment

- A total of 225 babies have been followed to date, 120 have weaned with an average HOT duration of 77 days ± 59 days

- Enrollment estimates predicted about 66 infants being enrolled per month, enrollment for the past month was 11

Data Queries

- Data queries have all been sent out

- Please get them back to Katie within the next 10 days

- If you have any questions, Katie likely has answers

Cost of Implementation Analysis

- Our submission to PCORI for additional funding to analyze the cost of implementing the RHO Program was awarded

- A survey will be distributed to site PIs in June/July

- Sites will be randomly queried at two time points to collect data and information on the time spent interpreting RHO results, calling families, documenting, and responding to RHO recommendation emails

- For any questions, please reach out to Heather

Miscellaneous Reminders

- Please email Katie when a new baby is enrolled in the program. She needs their oximeter serial number to be able to track their data.

- When the recommendation is to maintain, patients can be contacted through the EMR instead of phone calls at the discretion of your site.

- If you have any difficulties with REDCap or general questions, please reach out to Katie (Katherine.Edeburn@umassmed.edu)

- Heather has returned full-time to PA School. If your question requires prompt attention, please email Katie or the RHO Program central email (RHOprogram@umassmed.edu)

Next Investigator Meeting will be on July 6th at 4pm EST